## Overview in MM_F
|  |  | PC | QM |  |  |  | HEI |  |  |  |  | Multipliers |  | End User Reps
| Partners |  | AAA | BBB | CCC | DDD | EEE | FFF | GGG | HHH | III | JJJ | KKK | LLL | MMM | NNN | OOO
WP | Member state |  | IE | DE | IE | SL | DE | IT | LT | HR | PL | LV | LV | ES | IT | BE | ES
Tasks |  | Lead | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total | %
WP1 | Project management and coordination, ethics | 1 | 7.45 | 4.5 | 1 | 1 | 1 | 1 | 1 | 0.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 24.2 | 5.663%
1.1 | Management of the contractual commitments and financial control, establish Project Boards and publish the Project Manual (PM) | 1 | PC AAA IE: 2; QM BBB DE: 0.75 | 2.75
1.2 | Establishing overall Quality Management Processes, Standards and Measures | 2 | 1 | 1.25 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.05 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 4.7
1.3 | Regular monitoring and reporting the overall project development, progression and activities, internally and to the CEC | 1 | PC AAA IE: 2.75; QM BBB DE: 1.75 | 4.5
1.4 | Agreeing an overall Ethics Management Plan for the project and submission of local ethics forms where required | 1 | 0.5 | 0.15 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.05 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 3.1
1.5 | Preparing and attending 3 Project Board Meetings (kick-off, mid-term & project closing) plus bi-monthly virtual meetings | 1 | 1.2 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.15 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 9.15
| No. of Persons travelling for this WP |  | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 48
| Other costs for this WP | [16 empty] | 0
WP2 | Dissemination & establishing sustainability | 12 | 4.4 | 2.7 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.05 | 2.05 | 2.8 | 9 | 2.05 | 47.45 | 11.1%
2.1 | Implementing, maintaining and continually updating a project website and community of practice | 12 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 1.8 | 0.2 | 4.9
2.2 | User friendly CI branding and design (Logo, website, policy briefs, academic posters, …) | 12 | PC AAA IE: 0.25; QM BBB DE: 0.25; End User Reps NNN BE: 1 | 1.5
2.3 | Developing and publising a Communications and Sustainability Strategy with a BMC for post-project activities | 12 | 0.5 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1.25 | 0.25 | 5.75
2.4 | Ongoing outreach and engagement with key stakeholders (media, community groups etc.) | 12 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.75 | 0.25 | 4.25
2.5 | Promotion & dissemination via stakeholder workshops, seminars & international conferences | 12 | 0.8 | 0.35 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 3.1 | 0.75 | 13.25
2.6 | Organising and running a workshop with Accreditation Agencies | 1 | 0.35 |  | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  |  | 0.25 |  |  | 2.6
2.7 | Organising and running a final conference | 1 | 0.5 | 0.25 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.1 | 0.1 | 0.35 | 0.1 | 0.1 | 4.3
2.8 | Relevant project results made freely available according to FAIR principles | 1 | 0.75 | 0.15 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.5 | 0.5 | 0.25 | 6.65
2.9 | Scientific publications | 1 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.5 | 0.25 | 4.25
| No. of Persons travelling for this WP |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 58
| Subcontracting |  | End User Reps NNN BE: 12400 | 12400
| Open access publication fees |  | 3000 |  | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 |  |  | 3000 | 3000 |  | 33000
| Conference attendance |  | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 30000
| Other costs for this WP |  | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 30000
WP3 | Evaluation | 10 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 2.5 | 1.75 | 1.75 | 1.75 | 27 | 6.318%
3.1 | Evaluation of solution architecture designed in WP4 | 10 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.5 | 0.35 | 0.35 | 0.35 | 5.4
3.2 | Evaluation of training module and delivery path designed in WP5 | 10 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.5 | 0.35 | 0.35 | 0.35 | 5.4
3.3 | Evaluation of platform implemented in WP6 | 10 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.5 | 0.35 | 0.35 | 0.35 | 5.4
3.4 | Evaluation of localised training modules implemented in WP7 | 10 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.5 | 0.35 | 0.35 | 0.35 | 5.4
3.5 | Evaluation of module content and delivery with module alumni in WP8 | 10 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.5 | 0.35 | 0.35 | 0.35 | 5.4
| No. of Persons travelling for this WP | [16 empty] | 0
| Other costs for this WP | [16 empty] | 0
WP4 | Survey and analysis training needs per country and per sector to inform module content and delivery | 5 | 5.75 | 9.35 | 4.5 | 4.5 | 10.25 | 4.5 | 4.5 | 4.5 | 4.5 | 4.5 | 2.65 | 2.65 | 2.9 | 2.65 | 2.9 | 70.6 | 16.52%
4.1 | Develop survey instrument to assess digital literacy, resilience, service delivery and CPD access | 2 | 1 | 7 | 1 | 1 | 2.5 | 1 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 18.75
4.2 | Running 4.1 in partner regions | 5 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 16
4.3 | Analysis of 4.2 for training needs per country, sector, target groups and thematic focus referenced against EU Pact for Skills | 5 | 0.5 |  | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 6.25
4.4 | Mapping of existing continuous training and professional development training possibilities referenced to 4.2 & 4.3 | 5 | 0.5 |  | 0.5 | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 0.25 |  | 0.25 | 6
4.5 | Gap analysis referenced to 4.1 - 4.4 | 5 | 0.25 |  | 0.25 | 0.25 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | [5 empty] | 3
4.6 | Co-creation with stakeholders referencing "real world" competency skills credentialling referenced to 4.5 | 1 | 2 | 1 | 1 | 1 | 1.25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 16.25
4.7 | Generating WP summary report and performing Quality Gate | 5 | 0.5 | 0.35 | 0.25 | 0.25 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 4.35
| No. of Persons travelling for this WP | [16 empty] | 0
| Subcontracts | [16 empty] | 0
| Other costs for this WP | [16 empty] | 0
WP5 | Content development of four modules to deliver upskilling and reskilling | 4 | 10.85 | 2.35 | 6.85 | 18.25 | 7.35 | 6.85 | 6.85 | 6.85 | 6.85 | 6.85 | 2.15 | 2.75 | 1.15 | 1.15 | 1.15 | 88.25 | 20.65%
5.1 | Define integrated micro-credentialling approach with CPD | 1 | 2.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 13.5
5.2 | Referenced to WP4 define and develop content for modules 1-4 | 4 | 3 | 1.5 | 2 | 4 | 2.5 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0.5 | 0.5 | 0.5 | 26.5
5.3 | Define inputs and outcomes | 4 | 1 |  | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 |  |  |  | 11
5.4 | Transforming content into multimedia presentations as required | 4 | 2 |  | 1 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | [5 empty] | 17
5.5 | Define assessments | 4 | 0.5 |  | 0.5 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 5.5
5.6 | Seek accreditation through academic partner institutions | 1 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 0.5 |  |  |  | 10
5.7 | Generating WP summary report and performing Quality Gate | 4 | 0.35 | 0.35 | 0.35 | 0.75 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.35 | 0.15 | 0.25 | 0.15 | 0.15 | 0.15 | 4.75
| No. of Persons travelling for this WP | [16 empty] | 0
| Subcontracts | [16 empty] | 0
| Other costs for this WP | [16 empty] | 0
WP6 | Design & implement a delivery platform with augmented and virtual reality features | 1 | 21.5 | 0.95 | 2.65 | 3.9 | 2.65 | 2.65 | 2.65 | 2.65 | 2.65 | 2.65 | 2.65 | 4.15 | 2.3 | 2.3 | 4.8 | 61.1 | 14.3%
6.1 | Identify and adapt most commonly used delivery platforms | 1 | 3 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 5.4
6.2 | User Requirements Definition for the VR Pan European Healthcare training metaverse | 1 | 2 | 0.1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 5.35
6.3 | Identification of system / hardware requirements for the Healthcare training metaverse | 1 | 2.5 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 5.1
6.4 | Design and Development of VR Metaverse training Modules | 1 | 4 |  | 0.75 | 2 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 0.5 | 0.5 | 0.5 | 14.25
6.5 | Developing a virtual hospital data model based on the new Mutualia Hospital under construction | 1 | PC AAA IE: 3; Multipliers LLL ES: 1.5; End User Reps OOO ES: 2.5 | 7
6.6 | Testing, Improvement and Validation (standalone) | 1 | 3 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 9.75
6.7 | Pilot roll out support | 1 | 3 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 9.75
6.8 | Generating WP summary report and performing Quality Gate | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 4.5
| No. of Persons travelling for this WP | [16 empty] | 0
| Subcontracts | [16 empty] | 0
| Other costs for this WP |  | 4000 |  | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 |  |  |  |  | 4000 | 40000 | 4000
WP7 | Localising the module content into partner regions and testing the language versions with selected trainees | 6 | 5.25 | 0.5 | 2.75 | 5.5 | 5.5 | 8 | 5.5 | 5.5 | 5.5 | 5.5 | 1 | 3 | 2 | 0.75 | 3 | 59.25 | 13.86%
7.1 | Translating common core module content into partner panguages | 6 | 0.25 | 0.25 | 0.25 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 0.5 | 1.5 | 0.5 | 0.25 | 1.5 | 20
7.2 | Translating the Platform interface and messages into required partner languages | 1 | 2.5 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 |  |  |  | 10.5
7.3 | Select volunter trainees to test localised modules on the platform (w/o PO) | 6 | 1 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 |  |  | 1 |  | 1 | 11.5
7.4 | Improve module content delivery based on reslts from 7.3 | 6 | 1 |  | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1 | [5 empty] | 9.5
7.5 | Generating WP summary report and performing Quality Gate | 6 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7.75
| No. of Persons travelling for this WP | [16 empty] | 0
| Subcontracts | [16 empty] | 0
| Other costs for this WP | [16 empty] | 0
WP8 | Delivering and validating the modules with target group participants | 9 | 4 | 0.25 | 4 | 4.25 | 4.25 | 4.25 | 4.25 | 4.25 | 6.75 | 4.25 | 1.1 | 1.45 | 1.4 | 1.4 | 3.65 | 49.5 | 11.58%
8.1 | Promoting the modules through the participating HEI and Multipiers | 9 | 0.5 |  | 0.5 | 0.75 | 0.75 | 0.75 | 0.75 | 0.75 | 1.5 | 0.75 | 0.5 | 0.5 | 1 | 1 | 1 | 11
8.2 | Deliver each module to at least 100 learners drawn from the target groups with a total of 500 or more | 9 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 0.5 | 0.35 | 0.25 | 0.25 | 2 | 22.35
8.3 | Adjust module(s) based ob feedback received from Evaluation WP | 9 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 |  | 0.35 |  |  | 0.5 | 10.35
8.4 | Generating WP summary report and performing Quality Gate | 9 | 0.5 | 0.25 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.75 | 0.5 | 0.1 | 0.25 | 0.15 | 0.15 | 0.15 | 5.8
| No. of Persons travelling for this WP | [16 empty] | 0
| Subcontracts | [16 empty] | 0
| Other costs for this WP |  | PC AAA IE: 3000; QM CCC IE: 3000; QM DDD SL: 3000; QM EEE DE: 3000; HEI FFF IT: 3000; HEI III PL: 3000; End User Reps OOO ES: 3000 | 21000
10.7 | [17 empty] | 0
|  | Person/Months | 60.95 | 22.35 | 26.3 | 41.95 | 35.55 | 31.8 | 29.3 | 28.55 | 31.8 | 29.3 | 14.35 | 19.55 | 15.3 | 20 | 20.3 | 427.35
|  | Average PM Cost | 5275 | 6400 | 5440.75 | 4565 | 5225 | 4350 | 3200 | 4350 | 4100 | 3040 | 2459 | 6241.3 | 5759 | 5282 | 4720.0651
10.7
|  | Labour Costs | 321511.25 | 143040 | 143091.725 | 191501.75 | 185748.75 | 138330 | 93760 | 124192.5 | 130380 | 89072 | 35286.65 | 122017.415 | 88112.7 | 105640 | 95817.3218 | 2007502.0618
|  | Subcontracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12400 | 0 | 12400
|  | Travel costs | 7500 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 5250 | 3750 | 79500
|  | Other Costs | 14000 | 4000 | 14000 | 14000 | 14000 | 14000 | 11000 | 11000 | 14000 | 11000 | 4000 | 4000 | 7000 | 7000 | 7000 | 150000
|  | TOTAL | 343011.25 | 152290 | 162341.725 | 210751.75 | 204998.75 | 157580 | 110010 | 140442.5 | 149630 | 105322 | 44536.65 | 131267.415 | 100362.7 | 130290 | 106567.3218 | 2249402.0618
| Indirect Costs | 7% | 24010.7875 | 10660.3 | 11363.9207 | 14752.6225 | 14349.9125 | 11030.6 | 7700.7 | 9830.975 | 10474.1 | 7372.54 | 3117.5655 | 9188.7191 | 7025.389 | 9120.3 | 7459.7125 | 157458.1443
|  | Approximate Budget | 367022.0375 | 162950.3 | 173705.6457 | 225504.3725 | 219348.6625 | 168610.6 | 117710.7 | 150273.475 | 160104.1 | 112694.54 | 47654.2155 | 140456.1341 | 107388.089 | 139410.3 | 114027.0344 | 2406860.2062
|  | calciulated funding according to EU DBT | 293408.83 | 131430.23 | 156263.29 | 190658.87 | 143352.03 | 137909.29 | 92989.27 | 95779.83 | 142851.27 | 87908.91 | 43018.27 | 127715.19 | 104071.61 | 114400.11 | 114688.87 | 1976445.87
Note on B26: ====== ID#AAAAYbz07mE (2022-04-20 12:55:31) Change according to capacity -Florian Scheibein
Note on A28: ====== ID#AAAAYbz07mA (2022-04-20 12:55:31) Change -Florian Scheibein

## GANTT
| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | +1 | +2
WP1 | Project management and coordination, ethics | bar: 1 to 15; 17 to +1
1.1 | Management of the contractual commitments and financial control, establish Project Boards and publish the Project Manual (PM) | bar: 1 to 2; 13 to 14; 25 to 26
1.2 | Establishing overall Quality Management Processes, Standards and Measures
1.3 | Regular monitoring and reporting the overall project development, progression and activities, internally and to the CEC
1.4 | Agreeing an overall Ethics Management Plan for the project and submission of local ethics forms where required | bar: 1 to 3; 17 to 18
1.5 | Preparing and attending 3 Project Board Meetings (kick-off, mid-term & project closing) plus bi-monthly virtual meetings | bar: 1; 18
WP2 | Dissemination & establishing sustainability
2.1 | Implementing, maintaining and continually updating a project website and community of practice | bar: 1 to 30
2.2 | User friendly CI branding and design (Logo, website, policy briefs, academic posters, …) | bar: 3 to 5; 24 to 27
2.3 | Developing and publising a Communications and Sustainability Strategy with a BMC for post-project activities | bar: 4 to 6; 13 to 15; 28 to 30
2.4 | Ongoing outreach and engagement with key stakeholders (media, community groups etc.) | bar: 4 to 30
2.5 | Promotion & dissemination via stakeholder workshops, seminars & international conferences | bar: 13 to 30
2.6 | Organising and running a workshop with Accreditation Agencies | bar: 13 to 16
2.7 | Organising and running a final conference | bar: 28 to 30
2.8 | Relevant project results made freely available according to FAIR principles | bar: 13 to 30
2.9 | Scientific publications | bar: 13 to 30
WP3 | Evaluation
3.1 | Evaluation of solution architecture designed in WP4 | bar: 10 to 12
3.2 | Evaluation of training module and delivery path designed in WP5 | bar: 18 to 20
3.3 | Evaluation of platform implemented in WP6 | bar: 21 to 23
3.4 | Evaluation of localised training modules implemented in WP7 | bar: 22 to 24
3.5 | Evaluation of module content and delivery with module alumni in WP8 | bar: 28 to 30
WP4 | Survey and analysis training needs per country and per sector to inform module content and delivery | bar: 1 to 30
4.1 | Develop survey instrument to assess digital literacy, resilience, service delivery and CPD access | bar: 1 to 5
4.2 | Running 4.1 in partner regions | bar: 5 to 6
4.3 | Analysis of 4.2 for training needs per country, sector, target groups and thematic focus referenced against EU Pact for Skills | bar: 6 to 7
4.4 | Mapping of existing continuous training and professional development training possibilities referenced to 4.2 & 4.3 | bar: 7 to 8
4.5 | Gap analysis referenced to 4.1 - 4.4 | bar: 8 to 9
4.6 | Co-creation with stakeholders referencing "real world" competency skills credentialling referenced to 4.5 | bar: 9 to 10
4.7 | Generating WP summary report and performing Quality Gate | bar: 10 to 11
WP5 | Content development of four modules to deliver upskilling and reskilling | bar: 1 to 30
5.1 | Define integrated micro-credentialling approach with CPD | bar: 2 to 11
5.2 | Referenced to WP4 define and develop content for modules 1-4 | bar: 7 to 14
5.3 | Define inputs and outcomes | bar: 9 to 14
5.4 | Transforming content into multimedia presentations as required | bar: 9 to 16
5.5 | Define assessments | bar: 14 to 17
5.6 | Seek accreditation through academic partner institutions | bar: 14 to 18
5.7 | Generating WP summary report and performing Quality Gate | bar: 18 to 19
WP6 | Design & implement a delivery platform with augmented and virtual reality features | bar: 1 to 30
6.1 | Identify and adapt most commonly used delivery platforms | bar: 7
6.2 | User Requirements Definition for the VR Pan European Healthcare training metaverse | bar: 7 to 8
6.3 | Identification of system / hardware requirements for the Healthcare training metaverse | bar: 7 to 9
6.4 | Design and Development of VR Metaverse training Modules | bar: 9 to 14
6.6 | Testing, Improvement and Validation (standalone) | bar: 14 to 18
6.7 | Pilot roll out support | bar: 17 to 22
6.8 | Generating WP summary report and performing Quality Gate | bar: 21 to 22
WP7 | Localising the module content into partner regions and testing the language versions with selected trainees | bar: 1 to 30
7.1 | Translating common core module content into partner panguages | bar: 13 to 18
7.2 | Translating the Platform interface and messages into required partner languages | bar: 13 to 18
7.3 | Select volunter trainees to test localised modules on the platform (w/o PO) | bar: 17 to 21
7.4 | Improve module content delivery based on reslts from 7.3 | bar: 20 to 22
7.5 | Generating WP summary report and performing Quality Gate | bar: 22 to 23
WP8 | Delivering and validating the modules with target group participants | bar: 1 to +1
8.1 | Promoting the modules through the participating HEI and Multipiers | bar: 19 to 22
8.2 | Deliver each module to at least 100 learners drawn from the target groups with a total of 500 or more | bar: 22 to 28
3.5 | Evaluation of module content and delivery with module alumni in WP8 | bar: 27 to 29
8.3 | Adjust module(s) based ob feedback received from Evaluation WP | bar: 28 to 30
8.4 | Generating WP summary report and performing Quality Gate | bar: 29 to 30
DR | WP Delivery Reports
IR / FR | Interim & Final Report
QG | Quality Gates
M | Milestones
N | Newsletter

## CompactGANTT
| Project Quarters | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | +1
WP1 | Project management and coordination, ethics | bar: 1 to +1
WP2 | Dissemination & establishing sustainability | bar: 1 to 10
WP3 | Evaluation
WP4 | Survey and analysis training needs per country and per sector to inform module content and delivery | bar: 1 to 10
WP5 | Content development of four modules to deliver upskilling and reskilling | bar: 1 to 10
WP7 | Localising the module content into partner regions and testing the language versions with selected trainees | bar: 1 to 10
WP6 | Design & implement a delivery platform with augmented and virtual reality features | bar: 1 to 10
WP8 | Delivering and validating the modules with target group participants | bar: 1 to 10
IR/FR | Interim/Final Report
DR | Deliverable Summary Report
CP | Comminication Plan with Business Model Canvas Release 1-3

## Labour rates
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager |  | 10200 | 5% | 510 | Manager |  | 4400 | 5% | 300
Sen. Researcher |  | 7500 | 25% | 1875 | Sen. Researcher |  | 3900 | 25% | 2100
Jun. Researcher |  | 3850 | 25% | 962.5 | Jun. Researcher |  | 2700 | 25% | 600
Trainer/teacher |  | 4350 | 20% | 870 | Trainer/teacher |  | 2100 | 20% | 600
Technician |  | 4200 | 20% | 840 | Technician |  | 1500 | 20% | 600
Admin |  | 4350 | 5% | 217.5 | Admin |  | 1350 | 5% | 150
|  | Av- PM 4 Calc | 100% | 5275 |  |  | Av- PM 4 Calc | 100% | 4350
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager | 320 | 6400 | 5% | 320 | Manager |  | 6000 | 5% | 300
Sen. Researcher | 320 | 6400 | 70% | 4480 | Sen. Researcher |  | 6000 | 25% | 1500
Jun. Researcher | 240 | 4800 | 0% | 0 | Jun. Researcher |  | 3000 | 25% | 750
Trainer/teacher | 320 | 6400 | 0% | 0 | Trainer/teacher |  | 3000 | 20% | 600
Technician | 320 | 6400 | 20% | 1280 | Technician |  | 4000 | 20% | 800
Admin | 320 | 6400 | 5% | 320 | Admin |  | 3000 | 5% | 150
|  | Av- PM 4 Calc | 100% | 6400 |  |  | Av- PM 4 Calc | 100% | 4100
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager | 300 | 6000 | 5% | 300 | Project Manager |  | 11240 | 5% | 562
Sen. Researcher | 200 | 7500 | 25% | 1875 | Sen. Researcher |  | 8082 | 35% | 2828.7
Jun. Researcher | 125 | 5900 | 25% | 1475 | Jun. Researcher |  | 4934 | 30% | 1480.2
Trainer/teacher | 150 | 3000 | 20% | 600 | Trainer/teacher |  | 4934 | 20% | 986.8
Technician | 200 | 4000 | 20% | 800 | Technician |  | 3836 | 5% | 191.8
Admin | 175 | 3500 | 5% | 175 | Admin |  | 3836 | 5% | 191.8
|  | Av- PM 4 Calc | 100% | 5225 |  |  | Av- PM 4 Calc | 100% | 6241.3
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager |  | 12982 | 5% | 649.1 | Manager | 165 | 3300 | 5% | 165
Sen. Researcher |  | 6822 | 25% | 1705.5 | Sen. Researcher | 144 | 3000 | 25% | 750
Jun. Researcher |  | 4878 | 25% | 1219.5 | Jun. Researcher | 124 | 2480 | 25% | 620
Trainer/teacher |  | 4397 | 20% | 879.4 | Trainer/teacher | 144 | 3000 | 20% | 0
Technician |  | 4018 | 20% | 803.6 | Technician | 200 | 4000 | 20% | 800
Admin |  | 3673 | 5% | 183.65 | Admin | 124 | 2480 | 5% | 124
|  | Av- PM 4 Calc | 100% | 5440.75 |  |  | Av- PM 4 Calc | 100% | 2459
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager | 255 | 5100 | 5% | 255 | Manager | 350 | 7000 | 5% | 350
Sen. Researcher | 240 | 4800 | 25% | 1200 | Sen. Researcher | 300 | 6000 | 55% | 3300
Jun. Researcher | 240 | 4800 | 25% | 1200 | Jun. Researcher | 0 | 0 | 0% | 0
Trainer/teacher | 240 | 4800 | 20% | 960 | Trainer/teacher | 0 | 0 | 0% | 0
Technician | 195 | 3900 | 20% | 780 | Technician | 233 | 4660 | 20% | 932
Admin | 170 | 3400 | 5% | 170 | Admin | 175 | 3500 | 20% | 700
|  | Av- PM 4 Calc | 100% | 4565 |  |  | Av- PM 4 Calc | 100% | 5282
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager | 300 | 6000 | 5% | 300 | Manager |  | 14382.3483 | 5% | 719.1174
Sen. Researcher | 300 | 6000 | 35% | 2100 | Sen. Researcher |  | 5210.6429 | 35% | 1823.725
Jun. Researcher | 150 | 3000 | 20% | 600 | Jun. Researcher |  | 3102.9453 | 20% | 620.5891
Trainer/teacher | 150 | 3000 | 20% | 600 | Trainer/teacher |  | 4121.8035 | 20% | 824.3607
Technician | 200 | 4000 | 15% | 600 | Technician |  | 3826.7753 | 15% | 574.0163
Admin | 150 | 3000 | 5% | 150 | Admin |  | 3165.1325 | 5% | 158.2566
|  | Av- PM 4 Calc | 100% | 4350 |  |  | Av- PM 4 Calc | 100% | 4720.0651
xxx | Day Rate | P. Month | Involved | calc cost | xxx | Day Rate | P. Month | Involved | calc cost
Manager | 100 | 2000 | 5% | 100 | Manager |  | 9900 | 5% | 495
Sen. Researcher | 200 | 4000 | 35% | 1400 | Sen. Researcher |  | 6060 | 65% | 3939
Jun. Researcher | 100 | 2000 | 20% | 400 | Jun. Researcher |  | 4900 | 25% | 1225
Trainer/teacher | 150 | 3000 | 20% | 600 | Trainer/teacher |  |  | 0% | 0
Technician | 200 | 4000 | 15% | 600 | Technician |  |  | 0% | 0
Admin | 100 | 2000 | 5% | 100 | Admin |  | 2000 | 5% | 100
|  | Av- PM 4 Calc | 100% | 3200 |  |  | Av- PM 4 Calc | 100% | 5759
xxx | Day Rate | P. Month | Involved | calc cost
Manager |  | 3300 | 5% | 165
Sen. Researcher |  | 3000 | 35% | 1050
Jun. Researcher |  | 2500 | 20% | 500
Trainer/teacher |  | 3000 | 20% | 600
Technician |  | 4000 | 15% | 600
Admin |  | 2500 | 5% | 125
|  | Av- PM 4 Calc | 100% | 3040