## PM Effort Table
|  |  | Lead | PQM | Partner | Partner
| Partners |  | IWSI | EUBEN | ESK | BEFO
WP | Member state |  | IE | DE | ES | LV
Tasks |  | Resp. | 1 | 2 | 3 | 4 | Total | %
| Project Management | 1 | 0.8 | 0.5 | 0.3 | 0.3 | 1.9 | 18.63%
A1 | Project Management | 1 | 0.8 | 0.5 | 0.3 | 0.3 | 1.9
| Transnational Project Meetings |  | 700 |  | 700 | 700 | 2100
| Labour Costs |  | 4608 | 2880 | 1728 | 780 | 9996
| accumulated management costs |  | 5308 | 2880 | 2428 | 1480 | 12096
| Operational Activities | 1 | 2.3 | 2.1 | 2.1 | 1.8 | 8.3 | 81.37%
A2 | Identifying CPD requirements of Member Organisations of the participating NGO | 2 | 0.4 | 0.8 | 0.4 | 0.4 | 2
A3 | Identifying and cataloguing relevant training materials for exchange between NGO | 4 | 0.3 | 0.5 | 0.3 | 0.8 | 1.9
A4 | Derive relevant CPD policies and write guidelines for their implementation in SME | 1 | 1.3 | 0.5 | 0.3 | 0.3 | 2.4
A5 | Workshops, seminars and project & networking website | 3 | 0.3 | 0.3 | 1.1 | 0.3 | 2
| Other costs (Multiplier Events, flyers, posters, exhibition space, networking campaigns, …) |  | 1584 | 1400 | 1400 | 1400 | 5784
| Labour Costs |  | 13248 | 12096 | 12096 | 4680 | 42120
| Operational activities accumulated costs |  | 14832 | 13496 | 13496 | 6080 | 47904
10.7
|  | Person/Months | 3.1 | 2.6 | 2.4 | 2.1 | 10.2
|  | Average PM Cost | 5760 | 5760 | 5760 | 2600
10.7
|  | Labour Costs | 17856 | 14976 | 13824 | 5460 | 52116
|  | Travel costs | 700 | 0 | 700 | 700 | 2100
|  | Other Costs | 1584 | 1400 | 1400 | 1400 | 5784
|  | TOTAL Budget | 20140 | 16376 | 15924 | 7560 | 60000

## PM in Task Costs
| EXCOURS |  | Lead | PQM | Partner | Partner
| Partners |  | IWSI | EUBEN | ESK | BEFO
WP | Member state |  | IE | DE | ES | LV |  | Costs
Tasks |  | Resp. | 1 | 2 | 4 | 3 | Total | per Task
0 | Project Management | 1 | 4608 | 2880 | 1728 | 780 | 9996
A1 | Project Management | 1 | 4608 | 2880 | 1728 | 780 | 9996
0 | Transnational Project Meetings | 0 | 700 |  | 700 | 700 | 2100
| Other costs for this WP | [5 empty] | 0
0 | accumulated management costs | 0 | 5308 | 2880 | 2428 | 1480 | 12096 | 12096
0 | Operational Activities | 1 | 13248 | 12096 | 12096 | 4680 | 42120
A2 | Identifying CPD requirements of Member Organisations of the participating NGO | 2 | 2304 | 4608 | 2304 | 1040 | 10256 | 13148
A3 | Identifying and cataloguing relevant training materials for exchange between NGO | 4 | 1728 | 2880 | 1728 | 2080 | 8416 | 8416
A4 | Derive relevant CPD policies and write guidelines for their implementation in SME | 1 | 7488 | 2880 | 1728 | 780 | 12876 | 12876
A5 | Workshops, seminars and project & networking website | 3 | 1728 | 1728 | 6336 | 780 | 10572 | 13464
0 | Other costs for Project |  | 1584 | 1400 | 1400 | 1400 | 5784
0 | Operational activities accumulated costs | 0 | 14832 | 13496 | 13496 | 6080 | 47904 | 60000
10.7 |  | 0
0 |  | Labour Costs | 17856 | 14976 | 13824 | 5460 | 52116
0 |  | Travel costs | 700 |  | 700 | 700 | 2100
0 |  | Other Costs | 1584 | 1400 | 1400 | 1400 | 5784
0 |  | TOTAL Budget | 20140 | 16376 | 15924 | 7560 | 60000
60000

## GANTT
|  | 2025 | [11 empty] | 2026
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| Project Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | +1 | +2
A1 | Project Management | bar: 2025 1 1 to 2026 8 +2
A2 | Identifying CPD requirements of Member Organisations of the participating NGO | bar: 2025 1 1 to 2025 7 7
A3 | Identifying and cataloguing relevant training materials for exchange between NGO | bar: 2025 5 5 to 2025 12 12
A4 | Derive relevant CPD policies and write guidelines for their implementation in SME | bar: 2025 10 10 to 2026 6 18
A5 | Workshops, seminars and project & networking website | bar: 2025 2 2 to 2026 6 18
I/FR | Interim & Final Report